## Dashboard
Student AI Tool — Progress Dashboard
Live counts pull from the WBS sheet — just update the Status column there.
Total Tasks | Not Started | In Progress | Blocked | Done | % Complete
41 | 41 | 0 | 0 | 0 | 0%
Per-Person Summary
Assignee | Total Tasks | Done | In Progress | Not Started | Blocked | Total Effort (d) | Effort Done (d)
Shivanshi | 12 | 0 | 0 | 12 | 0 | 16 | 0
Sreehitha | 12 | 0 | 0 | 12 | 0 | 17 | 0
Shreya | 10 | 0 | 0 | 10 | 0 | 14.5 | 0
Team | 7 | 0 | 0 | 7 | 0 | 9.5 | 0
Phase Progress
Phase | Total Tasks | Done | % Complete
Phase 0 | 6 | 0 | 0%
Phase 1 | 4 | 0 | 0%
Phase 2 | 6 | 0 | 0%
Phase 3 | 4 | 0 | 0%
Phase 4 | 4 | 0 | 0%
Phase 5 | 5 | 0 | 0%
Phase 6 | 4 | 0 | 0%
Phase 7 | 2 | 0 | 0%
Phase 8 | 6 | 0 | 0%

## WBS
Task ID | Task Name | Assignee | Phase | Start Day | End Day | Effort (d) | Depends On | Status | Notes / Acceptance Criteria | GitHub Issue
P0-TEAM1 | Finalize product requirements + system architecture diagram | Team | Phase 0 | D1 | D1 | 1 | — | Not Started | Written to docs/architecture.md — covers auth, ingestion, RAG, scheduling and quiz flow end to end.
P0-SRE1 | Repo scaffold — Next.js + backend service structure, Docker skeleton, .env template | Sreehitha | Phase 0 | D1 | D1 | 1 | — | Not Started | docker compose up boots an empty frontend + backend; matches the agreed folder structure.
P0-SRE2 | Database schema — users, documents, syllabus_topics, sessions, chat_messages, quiz_results | Sreehitha | Phase 0 | D1 | D2 | 1 | P0-SRE1 | Not Started | Migration creates all tables; ERD committed to docs/.
P0-SHI1 | Auth stack decision + login/signup wireframes | Shreya | Phase 0 | D1 | D1 | 1 | — | Not Started | Wireframes cover email/password plus at least one OAuth option; stack choice documented.
P0-SHR1 | LLM + vector-DB stack decision, API key / config management | Shivanshi | Phase 0 | D1 | D2 | 1 | — | Not Started | docs/architecture.md lists the chosen LLM API, embedding model and vector store, with cost/rate-limit notes.
P0-TEAM2 | Agree shared topic-tree JSON schema (subject → unit → topic → subtopic, mastery field) | Team | Phase 0 | D2 | D2 | 0.5 | P0-SRE2 | Not Started | Schema frozen in docs/schema.md; every downstream module builds against this exact shape.
P1-SHI2 | Login / Signup pages (Next.js) | Shivanshi | Phase 1 | D2 | D3 | 1.5 | P0-SHI1 | Not Started | New user can sign up, log in, log out; invalid credentials handled gracefully.
P1-SHI3 | Session handling + protected route middleware | Shivanshi | Phase 1 | D3 | D4 | 1 | P1-SHI2 | Not Started | Unauthenticated users are redirected to login; session persists across a page refresh.
P1-SRE3 | App shell — sidebar, chat window, upload panel (Next.js) | Sreehitha | Phase 1 | D2 | D3 | 1.5 | P0-SRE1 | Not Started | Responsive shell renders with placeholder chat + upload widgets wired to routes.
P1-SRE4 | Backend API scaffold + auth token verification | Sreehitha | Phase 1 | D3 | D4 | 1 | P0-SRE2, P1-SHI2 | Not Started | A protected endpoint rejects requests without a valid session token.
P2-SHR2 | File upload endpoint (PDF/image) + storage | Shreya | Phase 2 | D3 | D4 | 1 | P1-SRE4 | Not Started | Upload accepts pdf/png/jpg, stores the file, returns a document_id.
P2-SHR3 | PDF text extraction pipeline | Shreya | Phase 2 | D4 | D5 | 1 | P2-SHR2 | Not Started | Typed-PDF text is extracted with page numbers preserved.
P2-SHR4 | OCR for handwritten notes | Shreya | Phase 2 | D5 | D7 | 2 | P2-SHR2 | Not Started | A handwritten sample image returns readable transcribed text; low-quality scans get a confidence flag.
P2-SHI4 | LLM prompt — subject / syllabus / topic-tree extraction from parsed text | Shivanshi | Phase 2 | D4 | D6 | 2 | P0-TEAM2, P2-SHR3 (stub OK) | Not Started | Given sample notes, returns a topic-tree JSON that matches the frozen schema.
P2-SHI5 | Topic-tree persistence — store per-user syllabus | Shivanshi | Phase 2 | D6 | D7 | 1 | P2-SHI4, P0-SRE2 | Not Started | Topic tree is saved and retrievable by user_id + document_id.
P2-SRE5 | Upload UI feedback — progress bar, parsed-topic preview / confirm screen | Sreehitha | Phase 2 | D6 | D7 | 1.5 | P2-SHI4 | Not Started | User sees the extracted topics and can edit or confirm them before proceeding.
P3-SRE6 | Diagnostic question generator (LLM, capped question count) | Sreehitha | Phase 3 | D7 | D9 | 2 | P2-SHI5 | Not Started | Generates a capped number of questions (default ~8) spanning the topic tree.
P3-SRE7 | Adaptive question flow — next question depends on prior answers | Sreehitha | Phase 3 | D9 | D10 | 1.5 | P3-SRE6 | Not Started | Question 2+ selection visibly changes based on answer 1 in a manual test.
P3-SHI6 | Knowledge-level scoring — map answers to per-topic mastery | Shivanshi | Phase 3 | D9 | D10 | 1.5 | P3-SRE6 | Not Started | Every topic in the tree gets a 0–1 mastery score once the diagnostic completes.
P3-SHR5 | Diagnostic chat UI — Q&A flow inside the chat window | Shreya | Phase 3 | D9 | D10 | 1.5 | P1-SRE3, P3-SRE6 | Not Started | Questions render as chat messages; answers submit inline with a progress indicator.
P4-SHI7 | Scheduling algorithm — topic priority from mastery gaps + available time input | Shivanshi | Phase 4 | D10 | D12 | 2 | P3-SHI6 | Not Started | Given mastery scores, hours/day and an exam date, outputs an ordered daily topic plan.
P4-SHI8 | Schedule persistence + versioning | Shivanshi | Phase 4 | D12 | D13 | 1 | P4-SHI7 | Not Started | Regenerating a schedule keeps the previous version retrievable, not silently overwritten.
P4-SHR6 | Schedule UI — calendar / timeline view, editable | Shreya | Phase 4 | D11 | D13 | 2 | P4-SHI7 | Not Started | Student can view the plan by day/week and manually reorder or reschedule a topic.
P4-SRE8 | "Explain this schedule" LLM summary | Sreehitha | Phase 4 | D12 | D13 | 1 | P4-SHI7 | Not Started | Chat message explains why weak topics are front-loaded, referencing mastery scores.
P5-SRE9 | Vector store integration — embed syllabus + chat turns per user | Sreehitha | Phase 5 | D12 | D14 | 2 | P0-SHR1, P2-SHI5 | Not Started | Embeddings are written per user/document; a similarity query returns relevant chunks.
P5-SRE10 | RAG retrieval pipeline — relevant syllabus + history per query | Sreehitha | Phase 5 | D14 | D16 | 2 | P5-SRE9 | Not Started | Given a doubt, retrieval returns the correct syllabus topic plus related past turns in a test set.
P5-SHR7 | Doubt-answering endpoint — grounded answers citing syllabus topic | Shreya | Phase 5 | D14 | D15 | 1.5 | P5-SRE10 | Not Started | Answer references the specific syllabus topic/unit it draws from, not generic LLM knowledge.
P5-SHI9 | Long-term memory summarization — compress old sessions | Shivanshi | Phase 5 | D15 | D16 | 1.5 | P5-SRE9 | Not Started | After N turns, older history is summarized so context stays under the token budget.
P5-SHI10 | Chat UI polish — streaming responses, topic references, history view | Shivanshi | Phase 5 | D16 | D17 | 1.5 | P1-SRE3, P5-SHR7 | Not Started | Responses stream token-by-token; user can scroll back and reopen a past session.
P6-SHR8 | Quiz generator — LLM builds quiz from topic-tree + weak areas | Shreya | Phase 6 | D16 | D18 | 2 | P3-SHI6, P4-SHI7 | Not Started | Quiz weights questions toward topics with lower mastery scores.
P6-SHR9 | Auto-grading logic — objective + short-answer scoring | Shreya | Phase 6 | D18 | D19 | 1.5 | P6-SHR8 | Not Started | MCQs graded exactly; short answers scored via an LLM rubric with a written score + rationale.
P6-SRE11 | Quiz-taking UI + results screen | Sreehitha | Phase 6 | D17 | D19 | 1.5 | P6-SHR8 | Not Started | Student takes the quiz in-app and sees a results screen with per-question feedback.
P6-SHI11 | Score analysis — per-topic breakdown, weak-area flags | Shivanshi | Phase 6 | D19 | D20 | 1 | P6-SHR9 | Not Started | Results screen shows a per-topic score bar and flags topics below a mastery threshold.
P7-TEAM3 | Feedback loop — quiz results update mastery scores + trigger schedule regeneration | Team | Phase 7 | D19 | D21 | 2 | P6-SHI11, P4-SHI8 | Not Started | Low-scoring topics reappear earlier in a regenerated schedule with no manual intervention.
P7-SHI12 | "Repeat cycle" trigger — new diagnostic/quiz suggested after milestones | Shivanshi | Phase 7 | D21 | D22 | 1 | P7-TEAM3 | Not Started | After a schedule milestone or quiz, the assistant proactively suggests the next check-in.
P8-TEAM4 | Dockerize full stack — frontend, backend, DB, vector store, compose file | Team | Phase 8 | D20 | D22 | 2 | P0-SRE1 | Not Started | docker compose up brings up the entire stack from a clean checkout.
P8-SRE12 | CI pipeline — GitHub Actions lint/test on push | Sreehitha | Phase 8 | D20 | D21 | 1 | P0-SRE1 | Not Started | PRs show a pass/fail status; a broken build blocks merge.
P8-TEAM5 | End-to-end test — upload → syllabus → diagnostic → schedule → chat → quiz → replan | Team | Phase 8 | D22 | D23 | 1.5 | P7-TEAM3, P8-TEAM4 | Not Started | One clean walkthrough of the full loop with a real sample document, no manual DB edits.
P8-TEAM6 | Bug-fix pass from integration test | Team | Phase 8 | D23 | D24 | 1.5 | P8-TEAM5 | Not Started | All blocking issues resolved or explicitly deferred with a note.
P8-SHR10 | Deployment — frontend host + backend/Docker host | Shreya | Phase 8 | D23 | D24 | 1 | P8-TEAM4 | Not Started | App reachable at a public URL; env vars/secrets set on the host, not committed.
P8-TEAM7 | Demo dry-run + final polish | Team | Phase 8 | D24 | D24 | 1 | P8-TEAM6, P8-SHR10 | Not Started | Full run-through: signup, upload, diagnostic, schedule, chat doubt, quiz, replan — no errors.

## Critical Path
Task | Blocks | Note
P0-TEAM2 (topic-tree schema) | P2-SHI4, P3-*, P4-*, P5-*, P6-* | Every downstream module builds on this JSON shape — lock it Day 2, a mid-sprint change forces rework across the whole team.
P2-SHI4 (topic-tree extraction) | P2-SHI5, P3-SRE6, P5-SRE9 | Diagnostic questions, scheduling and RAG all need a real topic tree, not a stub, to be meaningfully tested.
P3-SHI6 (mastery scoring) | P4-SHI7, P6-SHR8 | Both the study schedule and quiz weighting depend on per-topic mastery scores existing first.
P5-SRE9 / P5-SRE10 (vector store + retrieval) | P5-SHR7, chat quality overall | If retrieval quality is poor, doubt-answering degrades to generic LLM answers with no syllabus grounding — test this early with real notes.
P7-TEAM3 (feedback loop) | P8-TEAM5 | The full requested loop — schedule → quiz → replan — can't be demoed end-to-end until this closes.

## Final Checklist
# | Check | Verification | Done?
1 | Sign up + log in works | New account created, session persists, logout clears it. | No
2 | Upload a typed PDF | Correct subject + topic tree extracted and shown for confirmation. | No
3 | Upload a handwritten note | OCR transcribes it and topics are extracted, with a confidence flag on messy scans. | No
4 | Diagnostic runs | A capped, adaptive set of questions is asked, not a fixed static list. | No
5 | Mastery scores generated | Every topic in the tree gets a 0–1 mastery score after the diagnostic. | No
6 | Study schedule generated | Plan is ordered by weak areas first and respects available time input. | No
7 | Schedule is editable | Student can reorder or reschedule a topic and it persists. | No
8 | Doubt-answering remembers context | A follow-up question in a later session correctly references an earlier one. | No
9 | Quiz generated + auto-graded | Quiz targets weak topics; results show a score and rationale per question. | No
10 | Feedback loop closes | A low quiz score visibly moves that topic earlier in a regenerated schedule. | No

## Open Risks
Risk | Notes
Handwriting OCR accuracy varies widely | Messy handwriting can silently produce a wrong topic tree — surface a confidence flag and let the student correct extracted topics before proceeding.
LLM cost / rate limits | Extraction, diagnostics, chat and quiz generation all call the LLM repeatedly — cache where possible and consider a cheaper model for simple classification steps.
English-only constraint | Add early language detection so non-English notes are rejected with a clear message instead of producing a garbled topic tree.
Context/token budget for long-term memory | Test the summarization strategy (P5-SHI9) explicitly — a bad summary can silently drop syllabus context the student needs later.
Scope size for a 3-person team | This is a full loop: auth + RAG + scheduling + quiz + adaptive replanning. If timeline slips, treat OCR and the auto-replan loop as the first things to descope, not core chat/schedule.